ELTEE SYDNEY

Sense to Broadcast
Migration Plan

Performance Periodwear That Came to Play

Reconciled PMO plan covering source precedence, native Broadcast configuration, SEO continuity, release controls and rollback.

Version: 1.2 | 29 August 2026

Status: Broadcast 155379237001 is live; Sense 152278204553 is retained as the rollback theme. Post-launch monitoring and controlled improvements remain open.

Delivery position: migration build and publication complete. Remaining effort is post-launch monitoring, tracking verification and separately approved collection, redirect and content improvements.

GOVERNING RULE: Broadcast, age-inclusive positioning, the Tori Training hero video and the approved homepage H1 direction are narrow overrides. All unaffected master_blueprint.txt requirements remain authoritative.

# 1. Executive summary

This plan controls the migration from Sense to Broadcast without treating a visual redesign as permission to change URLs, tracking, schema or production configuration. Continuity, reversibility and search-rank protection are release-blocking requirements.

## Confirmed decisions

Target theme: Broadcast.

Master positioning: age-inclusive performance periodwear.

Positioning line: Performance Periodwear That Came to Play.

Homepage H1 direction: retain “Performance Periodwear That Came to Play” in the hero and render it as the page’s single H1, subject to native capability and final HTML verification.

Primary shop architecture: Shop All, The Starting Lineup, Swim, Active, Everyday, Accessories and Bundles.

Teen SEO destination: retain and strengthen the Best Period Underwear for Teens landing page.

Implementation: native Broadcast settings, sections and app blocks first.

Production publication and other customer-visible changes require explicit approval.

## Release target

☐  Zero downtime during theme cutover.

☐  No avoidable loss of organic search visibility.

☐  Every priority URL, canonical, heading, schema object, tracking event and purchase path verified.

☐  Immediate rollback available if a material defect appears.

ACCURACY: No competent migration plan can guarantee that rankings will never fluctuate. The control objective is to prevent avoidable loss, detect defects quickly and reverse safely.

## Source precedence

| Priority | Source | Authority |
| --- | --- | --- |
| 1 | Explicit approved decisions after blueprint creation | Override only the conflicting blueprint provision. |
| 2 | master_blueprint.txt | Authoritative for every unaffected configuration, value, asset, layout and app requirement. |
| 3 | Verified live Shopify and analytics evidence | Confirms current state; does not silently override the blueprint. |
| 4 | Google Drive project repository | Primary working repository; migration plan verified. Partially operational pending remaining project files. |

# 2. Source-conflict register

The register must remain live throughout the migration. An unresolved conflict blocks only the configuration or release activity it affects, but no affected work may proceed without written resolution.

| ID | Conflict | Affected work | Resolution/status |
| --- | --- | --- | --- |
| SC-01 | Blueprint says Symmetry; approved target is Broadcast. | All theme-specific paths, sections, blocks and settings | RESOLVED: Broadcast governs. Map every affected requirement. |
| SC-02 | Blueprint homepage H1 is girls-only; approved positioning is age-inclusive. | Homepage copy and semantic heading | DIRECTION CONFIRMED: retain the positioning line in the hero and use it as the single H1 if native Broadcast output permits; verify rendered HTML. |
| SC-03 | Blueprint nominates best-period-underwear for cart cross-sell; Broadcast native upsell is automatic. | Cart drawer merchandising | UNRESOLVED: approve automatic recommendations or an existing app solution. |
| SC-04 | Blueprint specifies Symmetry Product Info blocks. | PDP block order and variant controls | UNRESOLVED: map and verify native Broadcast equivalents. |
| SC-05 | Blueprint requires two review-rating placements. | PDP UX and review schema | UNRESOLVED: verify visual need without duplicate schema. |
| SC-06 | Blueprint prescribes Leak_Proof_Trio assets; Broadcast homepage is already designed. | Homepage hero and responsive assets | RESOLVED: current Tori Training video supersedes the prescribed static hero assets. Verify crop, poster, performance and mobile output. |
| SC-07 | Blueprint says sans-serif, 100% scales; brand typography is more specific. | Global typography | UNRESOLVED: document exact approved Broadcast fonts and scales. |

## Required register fields

☐  Conflicting requirements

☐  Affected page, setting or implementation task

☐  Governing source

☐  Approved resolution

☐  Approver

☐  Resolution date

☐  Required downstream changes

☐  Verification evidence and status

H1 IMPLEMENTATION GATE: Keep “Performance Periodwear That Came to Play” visible in the hero. Broadcast currently renders it as H2 and the preview has no H1. Configure one H1 natively if possible, then verify the rendered HTML before launch.

# 3. Phase 0 and Phase 0A

## Phase 0: baseline and governance

☐  [15 min] Record Broadcast draft ID 155379237001, live Sense ID 152278204553 and Sense backup ID 153521913993. Reverify all three in Shopify before relying on them.

☐  [45 min] Create the migration register with one row per current URL, template and integration.

☐  [45–60 min] Export products, variants, collections, pages, blogs, redirects, navigation and available theme settings.

☐  [45 min] Export Search Console data for 16 months and 90 days by page and query, including indexing and link reports.

☐  [45 min] Record Shopify and GA4 organic landing-page sessions, revenue, conversion and events for settled comparison periods.

☐  [20 min] Set a 24-hour content freeze before launch and name the launch and rollback decision owners.

## Phase 0A: blueprint reconciliation

☐  [20 min] Replace the Symmetry target with Broadcast in the working implementation map. Do not edit the read-only attached source.

☐  [30–45 min] Identify every Symmetry-specific section, block, module, setting and Shopify Admin path.

☐  [60–90 min] Map each affected requirement to Broadcast’s native functionality and record verified, unsupported or unverified.

☐  [45–60 min] Confirm whether Broadcast supports every required product-page block, placement and variant setting.

☐  [45–60 min] Map the approved Tori Training video into Broadcast and compare desktop/mobile crop, poster, CTA, reduced-motion and performance output with the completed homepage.

☐  [30 min] Reconcile the blueprint typography settings with the approved brand typography.

☐  [30 min] Verify social links and app requirements and add each to the acceptance checklist.

☐  [30–45 min] For unsupported requirements, propose the smallest native or app-based alternative and obtain approval before code or material app changes.

## Blueprint mapping status

| Requirement | Broadcast mapping | Owner | Gate |
| --- | --- | --- | --- |
| Logo 80px and favicon | Likely native theme settings; reverify | Theme Settings | Verify |
| 1600px max page width | Confirm available Broadcast width control | Theme Settings | Unresolved |
| Cart drawer, notes, currency codes | Previously saved in draft; reverify | Theme Settings | Verify |
| Named cart cross-sell collection | Not supported by native Broadcast upsell | Theme Settings | Decision |
| Responsive hero assets | Approved Tori Training video in native Broadcast video/slideshow block | Visual Layouts | Verify |
| PDP block stack | Map to Broadcast product template | Visual Layouts | Verify |
| Apps and embeds | Enable only after purpose and duplication checks | Visual Layouts | Verify |
| H1 and schema | SEO stream validation | SEO Safety Checks | Block |

# 4. Stream ownership and handoffs

| Stream | Owns | Does not implement |
| --- | --- | --- |
| PMO Master Plan | Dependencies, source-conflict register, approvals, timing, resourcing, release readiness and status | Theme settings, page layouts or SEO configuration |
| Theme Settings | Typography, colours, cart behaviour, footer, global links and social links | Banner construction, PDP block order or SEO testing |
| Visual Page Layouts | Banners, responsive scaling, native sections, template blocks and homepage assets | Global settings or SEO approval |
| SEO Safety Checks | URLs, headings, metadata, canonicals, schema, redirects and pre/post validation | Theme styling or page-layout implementation |

## Handoff rule

☐  Record the finding in the source-conflict or issue register.

☐  Assign it to the responsible stream with the affected URL/template and evidence.

☐  Do not implement it in the wrong specialist chat.

☐  Return the verified result to PMO for dependency and release-status updates.

## Repository status

CONFIRMED: The designated WORKING DOCS folder is the primary project repository. The migration plan is present, opens correctly and is verified. The repository is partially operational, not yet a complete source base, until the reconciled blueprint, registers and QA evidence are added and verified.

☐  Add the reconciled blueprint, conflict register, URL register, QA evidence and launch record to the existing repository.

☐  Open and verify each uploaded file before changing repository status to operational.

☐  Until every required file is verified, use the uploaded plan plus attached project sources and written approved decisions under the precedence rules.

# 5. Delivery sequence and estimate

Estimated hands-on effort is 58 to 89 hours for the website migration, plus 2 to 4 hours for Barb acceptance testing. At six focused hours per day, allow 10 to 16 working days. Around normal trading activity, allow three to five weeks, followed by 28 days of monitoring.

| Phase | Work | Estimate | Exit gate |
| --- | --- | --- | --- |
| 0 | Baseline and governance | 3–4 h | Recoverable baseline complete |
| 0A | Blueprint reconciliation | 3–5 h | Affected requirements mapped and conflicts logged |
| 1 | Brand and global settings | 3–5 h | Theme Settings acceptance passed |
| 2 | Collections and navigation | 4–6 h | Collection architecture populated |
| 3 | Broadcast templates and PDP/PLP | 13–19 h | Native template acceptance passed |
| 4 | Landing pages and content | 8–14 h | All current pages triaged |
| 5 | SEO and schema | 7–10 h | Pre-launch comparison passed |
| 6 | Apps, tracking and Markets | 4–6 h | Events, consent and currency passed |
| 7 | Full QA | 8–12 h | No block or high defects |
| 8 | Launch | 2–3 h | Broadcast live and smoke-tested |
| 9 | Monitoring | 3–5 h | 28-day review complete |

CRITICAL PATH: Baseline → blueprint reconciliation → specialist implementation → SEO/schema comparison → tracking and Markets → QA → approval → publish → monitor.

# 6. Phase 1: Theme Settings

Owner: Theme Settings stream. Cross-stream layout and SEO findings must be handed off.

## Authoritative blueprint settings

| Setting | Required value | Broadcast action |
| --- | --- | --- |
| Logo | ELTEE_SYDNEY_FULL_COLOUR_SQUARE_LOGO.png; 80px desktop | Select asset and set native logo width |
| Favicon | favicon-32x32.png | Select in Theme settings |
| Typography | Sans-serif; heading 100%; body 100% | Reconcile with approved exact brand fonts before change |
| Page width | 1600px maximum | Confirm native Broadcast width setting |
| Cart | Drawer | Set cart type to drawer |
| Cart notes | Enabled | Enable order note |
| Currency | Show currency code | Enable and test by market |
| Predictive search | Disabled | Disable and test standard search |
| Facebook | facebook.com/eltee.sydney | CONFIRMED 27 Aug: retain exact URL |
| Instagram | instagram.com/eltee.sydney | CONFIRMED 27 Aug: retain exact URL |
| TikTok | tiktok.com/@eltee.sydney | CONFIRMED 27 Aug: retain exact URL |
| Other socials | YouTube, X/Twitter, Pinterest, Snapchat blank | Omit from fields |

## Click path

☐  Shopify Admin → Online Store → Themes → Broadcast draft → Customise → Theme settings.

☐  Open Logo, Typography, Layout, Cart, Search and Social media settings as mapped above.

☐  Save the unpublished draft, reload the editor and verify each value persisted.

☐  Record screenshot or setting evidence in the Theme Settings acceptance record.

## Cart cross-sell decision

DECISION REQUIRED: The blueprint asks the cart to recommend products from the named collection best-period-underwear. Broadcast’s native cart recommendation block chooses products automatically and does not let you nominate that collection. This is a merchandising-control decision, not an SEO risk by itself.

Option A, native Broadcast: accept Shopify’s automatic recommendations. Lowest maintenance, but product selection is not controlled.

Option B, existing Essential Upsell app: use a curated offer if the app can target the cart drawer without duplicating Broadcast recommendations. Best choice if exact products matter.

Option C, custom Liquid: not approved unless both native and existing-app options fail. It adds maintenance and rollback risk.

Recommended test: preview automatic recommendations on five representative carts. If the products are sensible, keep native. If not, verify Essential Upsell in the unpublished theme and disable the duplicate native block.

# 7. Phase 2: collections and navigation

The collection architecture is an approved post-blueprint decision. It does not alter existing handles without SEO evidence.

| Navigation | Products/use | URL rule |
| --- | --- | --- |
| SHOP ALL | Complete sellable catalogue, including Starting Lineup products | Preserve /collections/all |
| SWIM | UnderSwim, G-Fit, bikini bottoms and SwimSync | Preserve current equity-bearing swim handle pending SEO review |
| ACTIVE | UnderAustin and UnderDance | Use strongest existing URL or create /collections/active-periodwear after evidence review |
| EVERYDAY | Bumpers Briefs, UnderShortie and UnderLiner | Create /collections/everyday-period-underwear if approved |
| ACCESSORIES | Wet Pouch and Stain Slayer | Create /collections/periodwear-accessories if approved |
| BUNDLES | Starter, Ready for Anything, combos and Encore | Preserve /collections/bundle-save |
| TEENS | Products genuinely suitable for teen fit and use | Preserve /collections/teen-period-underwear as a secondary SEO destination |
| CORE: THE STARTING LINEUP | Core performance periodwear range | Preserve /collections/the-starting-line-up |

## Implementation checklist

☐  [60 min] Shopify Admin → Products → Collections. Audit current membership, conditions, titles, descriptions and search performance.

☐  [60–90 min] Create only approved missing collections. Preserve handles wherever possible.

☐  [45 min] Order products deliberately and verify each product appears in the intended primary and secondary contexts.

☐  [30 min] Verify UnderAustin, UnderSwim and UnderDance variants through W18 where live inventory permits. Do not generalise that all products reach W18.

☐  [45 min] Shopify Admin → Content → Menus → Main menu. Add approved items and test desktop, mobile drawer and footer links.

## Homepage merchandising relationship

| Order | Homepage section | Link/behaviour |
| --- | --- | --- |
| 1 | Tori Training hero video | Visible positioning line; SHOP ALL → /collections/all |
| 2 | THE STARTING LINEUP | Featured core collection → /collections/the-starting-line-up |
| 3 | BUNDLE & SAVE | Promotional section → /collections/bundle-save |

Starting Lineup products remain in Shop All as well as the core collection. This is duplication by merchandising context, not a URL move.

# 8. Phase 3: Visual Page Layouts

Owner: Visual Page Layouts stream. Theme settings and SEO approval remain separate.

## Homepage asset reconciliation

| Viewport | Blueprint requirement | Required comparison |
| --- | --- | --- |
| Desktop | Current approved asset: Tori Training video | Retain video; verify desktop crop, poster frame, autoplay/mute, CTA contrast and performance |
| Mobile | Current approved asset: Tori Training video, responsive mobile crop | Verify 375px and 390px crop, focal point, text legibility, poster frame and reduced-motion fallback |

☐  Shopify Admin → Online Store → Themes → Broadcast draft → Customise → Home page.

☐  Open the native slideshow/video section and the Video block used by the completed homepage.

☐  Record current desktop/mobile assets, CTA, alignment, height, text-box and stacking settings.

☐  Compare each field against the blueprint. Do not overwrite the completed homepage until the variance is approved.

☐  Preview 375px, 390px, tablet and desktop widths. Hand the heading output to SEO Safety Checks.

## Homepage H1

APPROVED DIRECTION: Keep “Performance Periodwear That Came to Play” in the hero and use it as the homepage’s single H1. The current Broadcast preview renders it as H2 and contains no H1. First check for a native heading-tag control. If Broadcast cannot output H1 natively, document the limitation and seek approval for the smallest semantic-only code change.

## Product template mapping

| Blueprint order | Broadcast mapping status |
| --- | --- |
| 1. Breadcrumbs app block above Main Product | Verify app block can sit above native Main Product |
| 2. Product title | Expected native block; verify heading output |
| 3. Klaviyo average-rating stars | Verify app block and schema source |
| 4. Price | Expected native block; compare price/currency output |
| 5. Variant picker: pills/buttons, circle | Verify available Broadcast style and mobile usability |
| 6. Description | Map native description or accordion block |
| 7. Buy buttons; dynamic checkout enabled | Verify add-to-cart, dynamic checkout and cart drawer |
| 8. Secondary Klaviyo rating block | Decision required: preserve UX without duplicate widgets/schema |
| Below Main Product: Mod Bundles | Verify app block, discounts, inventory and cart line items |
| Template footer: full Klaviyo Reviews | Verify one full review display and correct schema attachment |

# 9. Templates and landing pages

## Broadcast template inventory

| Resource | Minimum templates | Acceptance |
| --- | --- | --- |
| Home | index | Approved content, one H1, working links and responsive assets |
| Product | default; performance; bundle only if needed | Variants, apps, purchase controls and schema intact |
| Collection | default; editorial/teen if needed | Filters, sort, copy, breadcrumbs and pagination |
| Page | default; size guide; FAQ; campaign; wholesale/operational | Correct heading, indexability, forms and links |
| Blog/article | default | Article history, links and structured data intact |
| System | cart, search, 404, password and gift card | No dead ends and correct branding |

☐  Inventory current template_suffix values for every product, collection and page.

☐  Create required Broadcast templates before resource assignment.

☐  Preview each template with a representative resource.

☐  Prepare the assignment list and verify the launch workflow using a safe test resource.

## Template wireframes

These are native-section content maps, not visual comps. Section order may vary only with an approved UX or SEO reason.

### Default page

| Order | Native section/block | SEO and UX rule |
| --- | --- | --- |
| 1 | Page title | One H1, concise and intent-matched |
| 2 | Intro rich text | Answer the purpose immediately |
| 3 | Main content sections | H2/H3 hierarchy; no heading skips |
| 4 | Supporting image/video | Descriptive alt text; controlled media weight |
| 5 | Related links/CTA | Link to relevant collection, product or policy |
| 6 | FAQ if useful | Visible answers; schema only when eligible |

### Default collection

| Order | Native section/block | SEO and UX rule |
| --- | --- | --- |
| 1 | Collection title and intro | One H1; preserve approved handle and canonical |
| 2 | Product grid | Filters, sort, availability and pagination work |
| 3 | Use-case guidance | Short H2 copy below or above grid as appropriate |
| 4 | Comparison or fit help | Reduce product-choice friction |
| 5 | Related collections | Internal links without keyword cannibalisation |
| 6 | FAQ/editorial support | Only content that serves collection intent |

### Default product

| Order | Native section/block | SEO and UX rule |
| --- | --- | --- |
| 1 | Breadcrumbs | One breadcrumb trail and one schema source |
| 2 | Media gallery | Images/video, alt text and mobile swipe |
| 3 | Product title, rating, price | Product title is H1; visible review evidence |
| 4 | Variants and buy buttons | Size/colour, availability, add to cart, dynamic checkout |
| 5 | Core description/benefits | Verified claims only |
| 6 | Fit, care, delivery accordions | Native blocks and clear labels |
| 7 | Bundles/related products | No duplicate cart or upsell widgets |
| 8 | Full reviews | One authoritative review/schema implementation |

### Default blog article

| Order | Native section/block | SEO and UX rule |
| --- | --- | --- |
| 1 | Article title and metadata | One H1; author/date where relevant |
| 2 | Hero image | Descriptive alt text and correct dimensions |
| 3 | Opening answer | Match query intent before brand narrative |
| 4 | Body | Logical H2/H3 structure and cited evidence |
| 5 | Product/context links | Relevant, restrained internal links |
| 6 | Related articles | Strengthen topic cluster and onward journey |

### Default landing page

| Order | Native section/block | SEO and UX rule |
| --- | --- | --- |
| 1 | Hero | One H1, audience/use case and primary CTA |
| 2 | Problem and proof | Outcome, evidence and verified claims |
| 3 | Featured product/collection | Direct route to purchase |
| 4 | How it works | Native media and concise steps |
| 5 | Comparison/fit guidance | Resolve objections and product choice |
| 6 | Reviews/authority | Visible proof; avoid duplicate review schema |
| 7 | FAQ | Visible, useful and schema-eligible if marked up |
| 8 | Final CTA and related links | No dead-end campaign page |

## Landing-page migration groups

| Group | Current pages | Action |
| --- | --- | --- |
| Fit/care | size charts, care info and demo videos | Retain or consolidate only with traffic, links and canonical evidence |
| Teen/first period | first period, pool and leak-free tips | Keep intent-specific wording and link to teen plus relevant collections |
| Sport/swim | sailing, competition, para and inclusive-swim campaign | Retain if indexed or strategically active; update products and positioning |
| Trust | reviews, mission, pricing promise, returns and FAQ | Rebuild with current proof, policies and age-inclusive master copy |
| Retail/wholesale | wholesale, pharmacy, stockists, locator and Erina | Verify details, forms, audience and indexability |
| Advocacy | Share the Dignity, Bloody Good Sport and join the team | Retain where current; remove unsupported claims |
| Operational/legal | contact, quick order, returns variants, privacy and terms | Preserve intended access, forms, URLs and footer links |

## Sport and swim search visibility, verified 27 August 2026

| Page | GSC, 25 May–24 Aug | Finding |
| --- | --- | --- |
| /pages/girls-periods-pool | 0 clicks; 256 impressions; position 7.3 | Visible but zero CTR. Rewrite title/meta and align intent. |
| /pages/period-inclusive-swim-campaign | 1 click; 106 impressions; CTR 0.9%; position 8.9 | Indexed with limited branded visibility. Strengthen non-brand intent and links. |
| /pages/comp-swimmers | 0 clicks; 0 impressions | Page appears in Google, but has no GSC demand/visibility in the period. |
| /pages/para-swimmers | 0 clicks; 0 impressions | Page appears in Google, but has no GSC demand/visibility in the period. |
| /pages/period-swim-underwear-for-sailing | 0 clicks; 0 impressions | In sitemap; search visibility not verified. Run URL Inspection and indexing checks. |

☐  Run URL Inspection for all five pages and record indexed status, canonical and last crawl.

☐  Map one primary query cluster per page so competition, club, para, sailing and campaign pages do not cannibalise each other.

☐  Improve title, H1, opening copy and meta description where impressions exist but CTR is weak.

☐  Add contextual links from Swim collection, UnderSwim products and relevant articles. No orphan campaign pages.

☐  Recheck GSC at 28 and 56 days. Retain, consolidate or expand based on settled evidence, not whether a page merely exists.

# 10. Teen landing-page SEO brief

The teen landing page is an intentional search and customer-use-case destination within an age-inclusive brand. It does not define the master positioning.

| Element | Working value/status |
| --- | --- |
| URL | Preserve /collections/teen-period-underwear |
| Canonical | Self-referencing .com.au canonical, subject to market validation |
| SEO title | Draft: Best Period Underwear for Teens ¦ Eltee Sydney |
| H1 | Draft: Best Period Underwear for Teens. SEO stream to verify and approve. |
| Meta description | Draft: Shop performance period underwear for teens, with options for school, sport, swimming and sleep. Find the right fit and protection at Eltee Sydney. |
| Audience | Teen wearer and parent buyer; direct, practical and non-childish |

## Native section order

☐  Short intent-matching introduction.

☐  Product finder by Swim, Active, Everyday and First Period use case.

☐  Fit and size guidance, stating W18 only where verified.

☐  Comparison table using verified protection and fit claims.

☐  Relevant reviews and proof.

☐  Care and washing guidance.

☐  Visible frequently asked questions.

☐  Internal links to collections, size guide, returns and supporting articles.

## Guardrails

Use the target phrase naturally in the title, H1 and opening copy after SEO approval.

Include only products genuinely suited to teen fit and use.

Do not promise wear hours, universal leak prevention or outcomes that are not verified.

Use FAQ schema only when visible content and current eligibility requirements are met.

# 11. SEO safety checks

Owner: SEO Safety Checks stream. Launch is blocked while a material SEO check is failed, missing or unverified.

## SEO migration is built into this plan

It operates before build, during Broadcast configuration, at launch and for 28 days afterwards. It is not a final tidy-up phase.

### Before creating a new page or collection

☐  Define search intent, target audience and primary query cluster.

☐  Check existing pages for overlap, rankings, backlinks and internal-link equity.

☐  Approve the URL handle before creation. Shopify resources are shared across themes, so a new page or collection is not automatically isolated inside the unpublished Broadcast theme.

☐  Draft SEO title, meta description, H1, canonical/indexation rule and internal links before publishing the resource to the Online Store channel.

☐  Assign the correct Broadcast template and expected schema type.

☐  Add the resource to the URL register and test it before linking it from navigation or the homepage.

☐  If replacing or consolidating content, complete the redirect-equity assessment before any URL change.

## Baseline and comparison

☐  [90 min] Crawl the live Sense store and record URL, status, title, meta description, H1, canonical, robots, internal links and schema types.

☐  [90 min] Repeat the crawl against accessible Broadcast preview URLs or immediately after controlled publication where preview limitations apply.

☐  [60 min] Compare all priority URLs and one representative URL for every unique template.

☐  [30 min] Confirm one purposeful H1 per indexable page. On the homepage, verify “Performance Periodwear That Came to Play” is the single H1.

☐  [45 min] Verify .com.au and .com domains and any market subfolders separately.

☐  [60–90 min] Fix broken internal links, placeholder # links, orphan priority pages and redirect chains.

## Structured-data continuity

| Page | Expected validation |
| --- | --- |
| Home | Organisation/WebSite entities where supported, with accurate name, URL, logo and profiles |
| Product | ProductGroup/Product, Offer, price, currency, availability, SKU, variants and legitimate ratings |
| Collection | BreadcrumbList and ItemList where supported, without duplicate chains |
| Article | Article/BlogPosting, dates, image, publisher and breadcrumbs |
| Pages | Breadcrumbs and FAQ only where visible and valid |

☐  Capture raw JSON-LD from Sense and Broadcast for representative templates.

☐  Run Google Rich Results Test and Schema.org Validator where accessible.

☐  Remove duplicate schema from theme, apps or CodeUp only after identifying the authoritative source.

☐  Verify review schema is supported by visible, legitimate review content.

☐  Verify ProductGroup and variant offers for UnderAustin, UnderSwim and UnderDance, including W18 where available.

### How the implementation task will verify schema

☐  Open one live Sense product for UnderAustin, UnderSwim and UnderDance. Save the raw JSON-LD from script[type='application/ld+json'] as the baseline evidence.

☐  Open the same product through the Broadcast preview. Capture the equivalent JSON-LD and identify whether the theme, Klaviyo, CodeUp or another app owns each Product, ProductGroup, Offer, Review and Breadcrumb object.

☐  Compare product name, canonical URL, SKU, price, currency, availability, variant URLs and size offers. Confirm W18 only where that live variant exists and is purchasable.

☐  Run the public URL through Google Rich Results Test and the JSON-LD through Schema.org Validator. Preview URLs may require browser inspection when Google cannot access them.

☐  Record PASS, FAIL or BLOCKED by template. Do not remove duplicate schema until the authoritative source is identified and rollback evidence is saved.

This is a guided implementation task. Sarah will not be expected to interpret raw JSON-LD unaided.

## Redirect rules

Before any URL change, record GSC clicks, impressions, ranking queries, backlinks, internal links, canonical status and the target page’s intent match.

Preserve handles by default. A design or navigation change is not a reason to change a URL.

Create a one-hop 301 only when the source URL will cease to resolve or content is genuinely consolidated.

Do not redirect an active Shopify resource instead of fixing it.

Test source, target, market and language behaviour before approval.

Changing live redirects requires explicit production approval.

No redirect is approved until the SEO value and target equivalence are documented in the redirect register.

# 12. Apps, tracking and Markets

## Blueprint app acceptance

| App | Blueprint requirement | Acceptance check |
| --- | --- | --- |
| CodeUp | Global embed ON | Inventory each snippet; retain only approved required code |
| Instafeed | Global embed ON | Load, crop, fallback and performance |
| Stoq | Global embed ON | Back-in-stock form, consent and unavailable variant |
| Essential Upsell | Global embed ON | Placement, discount, cart drawer and mobile |
| Klaviyo onsite | Global embed ON | Tracking, forms, consent and duplicate script risk |
| Barb | Global embed ON; #f2581f; BARB_3.png; Codex/OpenAI migration dependency | Verify endpoint, embed identity, bubble, consent, mobile placement and cutover status |
| Breadcrumbs | Block above Main Product | Position, links and one schema source |
| Mod Bundles | Block below Main Product | Selection, discount, inventory, cart and checkout |
| Klaviyo Reviews | Full-width template footer | Visible reviews and correct schema attachment |

## Barb migration dependency

| Item | Verified status | Website migration effect |
| --- | --- | --- |
| Repository | ESGEE-0562/shop-chat-agent | Codex is the maintenance surface |
| Migration change | Draft PR #10, branch codex/barb-openai-runtime | Runtime moves from Anthropic Messages to OpenAI Responses API |
| Production | Unchanged on commit 2fd5d67 | Do not alter the live embed or endpoint yet |
| Rollback | Keep CLAUDE_API_KEY and current deployment temporarily | Preserve existing live service until acceptance passes |
| Next gate | Approve isolated Render development service and smoke tests | May incur temporary Render charges; separate approval required |

☐  Complete isolated Render testing for product search, order lookup, sizing, returns, shipping, privacy and historical conversations.

☐  Confirm whether the Shopify app embed identifier and public widget endpoint remain unchanged after runtime cutover.

☐  If the endpoint changes, update only the unpublished Broadcast embed and test before production approval.

☐  Do not merge PR #10, deploy production or remove the Claude rollback path from this website migration task.

☐  After Barb production acceptance, verify the Broadcast app embed once on desktop and mobile and record the result in the launch checklist.

MIGRATION BOUNDARY AND ADMIN CHECK: The approval gate prevents app removal, live reconfiguration or production cutover without approval. The admin check is the read-only verification of which embeds are enabled, where they render and whether scripts duplicate. Draft-theme testing may proceed only within the approved unpublished scope.

## Tracking

☐  Verify GA4 page_view, view_item, view_item_list, select_item, add_to_cart, view_cart, begin_checkout and purchase.

☐  Verify Google Ads conversions and enhanced conversions where used.

☐  Verify Meta Pixel and Conversions API event IDs and deduplication.

☐  Verify Klaviyo onsite and checkout events.

☐  Confirm consent behaviour before non-essential tracking fires.

☐  Do not replace production tracking without explicit approval.

## Markets and currency

☐  Shopify Admin → Settings → Markets. Confirm .com.au and .com domains, countries, languages and currencies separately.

☐  Test prices, compare-at prices, discount codes, shipping messages and checkout currency by supported market.

☐  Verify canonicals and hreflang after market routing is confirmed.

☐  DNS changes require explicit approval.

# 13. Full QA

## Functional

☐  Header, announcement bar, menus, search, filters, sorting, pagination and footer links.

☐  Homepage hero, buttons, rails, article cards, newsletter and social feed.

☐  Product media, variants, size guide, prices, availability, reviews, accordions and add to cart.

☐  Cart drawer, quantity, removal, discounts, upsell, order note and checkout.

☐  Forms: contact, wholesale, newsletter, back in stock and campaigns.

☐  Accounts, policies, 404, empty search, empty cart and sold-out states.

## Mobile and accessibility

☐  Current iPhone Safari and Android Chrome critical purchase flow.

☐  Desktop Chrome and Safari, plus tablet portrait and landscape.

☐  Keyboard access, visible focus, labels, reading order, alt text, contrast and reduced-motion behaviour.

☐  Image sizing, lazy loading, video controls and material performance regressions.

## Content and SEO

☐  Age-inclusive master positioning and approved product-specific audience language.

☐  Homepage H1 equals “Performance Periodwear That Came to Play” and appears once in rendered HTML.

☐  No stale Symmetry implementation instructions remain in the working build.

☐  No unsupported materials, protection, absorbency or wear-hour claims.

☐  Correct title, meta, canonical, indexability, internal links and schema on every representative template.

☐  No unexplained 404s, placeholder links, orphan priority URLs or redirect chains.

# 14. Production approval gate

No irreversible or customer-visible action may occur without explicit approval.

## Explicit approval required

☐  Publishing the Broadcast theme

☐  Altering the live Sense theme

☐  Changing DNS or production domain routing

☐  Modifying live redirects

☐  Uninstalling or materially reconfiguring apps

☐  Deleting templates, sections or assets

☐  Replacing production tracking or analytics

☐  Changing checkout behaviour or customer data handling

☐  Adding custom Liquid to production theme code

## Pre-publish acceptance

☐  Every Phase 0A requirement affecting launch is reconciled.

☐  The homepage H1 is approved and verified once in rendered HTML.

☐  No unresolved BLOCK or HIGH defect remains.

☐  Priority URLs, metadata, canonicals, schema and internal links pass comparison.

☐  Apps, tracking, Markets, cart and checkout pass.

☐  Rollback theme, owner, trigger and decision process are recorded.

☐  Two-hour launch coverage and 28-day monitoring are scheduled.

CURRENT STATUS: LIVE. Broadcast 155379237001 was published on 29 August 2026. Immediate route, H1, canonical and structured-data smoke tests passed. Sense 152278204553 remains available for rollback.

# 15. Launch and rollback runbook

## T minus 24 hours

☐  Start content freeze and reconcile the migration and conflict registers.

☐  Duplicate/export the latest Sense state and record the rollback theme ID.

☐  Run final crawl, schema checks, link check and mobile purchase flow.

☐  Confirm all release blockers are closed with evidence.

☐  Obtain explicit approval to publish Broadcast.

## Publish window

☐  Shopify Admin → Online Store → Themes → Broadcast → Publish. Record timestamp and approver.

☐  Immediately test homepage, navigation, representative products, primary collections, teen landing, cart and checkout.

☐  Test .com.au and .com routing, prices and currency.

☐  Check live H1, canonical, robots and structured data.

☐  Verify add_to_cart, begin_checkout and purchase events without duplication.

☐  Annotate the launch in the PMO record and analytics notes.

## Rollback triggers

Checkout, add to cart or variant selection materially fails.

Primary domain, market routing or currency is wrong.

Widespread noindex, canonical or 404 errors appear.

Purchase tracking is absent or duplicated and cannot be isolated quickly.

A critical app blocks the purchase path.

ROLLBACK: Republish the recorded Sense backup, preserve evidence, then diagnose in the unpublished Broadcast theme. Do not delete the failed draft.

# 16. Post-launch monitoring

| When | Checks | Threshold/action |
| --- | --- | --- |
| 0–2 hours | Checkout, events, errors, 404s, domains, currency and core pages | Rollback for material purchase, domain or indexability failure |
| 24 hours | Shopify sales, GA4, ads signals and crawl anomalies | Fix isolated defects; compare with normal range |
| 72 hours | Indexing, canonicals, rich results and priority landing pages | Investigate template-wide movement or coverage errors |
| 7 days | Queries, landing pages, revenue, 404s and performance | Prioritise traffic- and revenue-impacting regressions |
| 14 days | Trends, crawl stats, schema and backlink destinations | Correct persistent technical or content mismatch |
| 28 days | Full review and issue closeout | Retire rollback theme only after approval |

☐  Organic sessions and revenue to priority landing pages

☐  Conversions and revenue by source against settled periods

☐  404 count and requested missing URLs

☐  Indexed/not-indexed movement and crawl anomalies

☐  Product/rich-result errors and warnings

☐  Purchase, checkout and add-to-cart counts and deduplication

☐  Site speed and critical errors by device

Do not judge SEO from one day. Use settled like-for-like periods and separate normal volatility from template-wide technical defects.

# 17. Final release checklist

## Authority and governance

☐  Conflict register complete; all launch-affecting conflicts resolved in writing.

☐  Google Drive status is recorded as partially operational until every required project file is uploaded and verified.

☐  All cross-stream dependencies returned to PMO with evidence.

☐  Production approval recorded for every customer-visible action.

## Brand and content

☐  Broadcast target and age-inclusive positioning applied.

☐  Positioning line retained in the homepage hero and verified as the single H1.

☐  Homepage H1 equals “Performance Periodwear That Came to Play” and appears once in rendered HTML.

☐  Teen language used only where intentional and useful.

☐  Every footer and CTA link resolves.

## Commerce and SEO

☐  Products, variants, collections, navigation, cart and checkout pass.

☐  Priority handles are retained; approved changes have tested one-hop redirects.

☐  Titles, metadata, canonicals, indexability and schema pass.

☐  No unexplained 404s, placeholder links, orphan pages or redirect chains.

☐  Teen landing page passes its approved SEO brief.

☐  GA4, Google Ads, Meta and Klaviyo events are verified without duplication.

NEXT ACTION: complete real-order tracking verification for Shopify order #51906, monitor Search Console after recrawl, and treat new collections, redirects, shared content, privacy and tracking changes as separate approval-gated post-launch work.

# 18. Reference sources

## Attached project sources

master_blueprint.txt

Project Management Office.txt

chat1_theme_settings_prompt.txt

chat2_visual_layouts_prompt.txt

chat3_seo_safety_prompt.txt

instructions.txt

## External references

Designated Google Drive project repository

Eltee Sydney sitemap

Shopify templates

Shopify URL redirects

Shopify SEO metadata

Shopify Markets domains and languages

## Evidence status

| Evidence | Status |
| --- | --- |
| Attached project sources | Available evidence base; read-only |
| Approved Broadcast and positioning decisions | Governing narrow overrides |
| Broadcast draft ID and prior saved settings | Historical verified snapshot; reverify before action |
| Google Drive folder | Operational repository. Current local control and evidence files extend beyond the earlier Drive snapshot; update Drive with this plan and the work-completed record. |
| Live store, Search Console, GA4 and Shopify | Must be refreshed at Phase 0 and launch |

The attached blueprint remains authoritative except where the approved Broadcast, age-inclusive positioning, Tori Training video and homepage H1 direction override it. Live SEO and Shopify evidence must be refreshed during implementation.

# 19. Verified implementation outcome

This section updates the original plan with the verified state at 29 August 2026. Where an earlier forecast, unresolved item or pre-launch status conflicts with this section, this verified outcome governs. The original planning content is retained for traceability.

## 19.1 Publication and rollback

Completed: Broadcast theme 155379237001 published as the live theme.

Completed: Sense theme 152278204553 retained unpublished for immediate rollback.

Completed: Final Sense snapshot captured with 549 files.

Completed: Publication completed without changing redirects, DNS, Markets, shared product data, apps or tracking configuration.

Completed: Immediate public routes on .com.au and .com returned HTTP 200.

Completed: Representative live H1, canonical and JSON-LD output passed the publication smoke test.

Completed: Paid Shopify order #51906 completed after publication.

## 19.2 Brand, theme and homepage

Completed: Age-inclusive positioning and the line Performance Periodwear That Came to Play adopted.

Completed: Homepage hero line implemented as the single H1 and visually reduced against imagery without changing its semantic role.

Completed: Tori Training video retained with native underlay after contrast sampling.

Completed: The Starting Line-Up and Bundles merchandising routes retained.

Completed: Real Blood Demo proof section added using approved copy and existing media.

Completed: Tested for Safety added as a native fourth homepage proof column.

Completed: Approved typography, colours, logo, favicon, cart drawer, currency display and social URLs retained.

## 19.3 Templates, commerce and content

Completed: Active product-template assignments mapped and product galleries standardised.

Completed: All 17 public product pages passed the one-H1 sweep.

Completed: Representative W18, cart and checkout hand-off checks passed on desktop and mobile.

Completed: Starter Bundle confirmed buyable as the relevant First Period Kit replacement destination.

Completed: Two Klaviyo review placements retained with one authoritative AggregateRating source on representative UnderSwim.

Completed: Quantity label, 404 H1, swatch/link and footer market-link corrections completed.

Completed: Tested for Safety rolled out to the 13 product-template families used by the public catalogue.

Completed: Tips to Ensure a Leak-Free Wear restored with native Broadcast sections, instructional images and current Barb contact route.

## 19.4 SEO, schema and markets

Completed: Search Console performance, indexing and link evidence captured for .com.au and .com.

Completed: URL, metadata-continuity, indexing-triage and redirect registers created.

Completed: Representative Sense-to-Broadcast URL, title, meta, H1, canonical, robots, links and schema comparison completed.

Completed: Article JSON-LD repaired and verified.

Completed: Owned visible breadcrumbs and one matching BreadcrumbList implemented for Product, Collection, Page and Article templates.

Completed: Representative external Rich Results and Schema.org checks passed with no reported errors or warnings.

Completed: Generic collection ItemList intentionally not recreated.

Completed: Stain Slayer retained on .com.au and removed from customer-facing .com navigation.

Completed: Existing Swim URL retained through launch; proposed replacement and redirect remain post-launch work.

## 19.5 Redirect preparation

Completed: 413 live Shopify redirects reconciled.

Completed: 84 chain candidates classified, with no loops and a five-hop maximum exported chain.

Completed: Deduplicated 66-row Shopify-format approval draft prepared.

Completed: Pre-activation integrity audit completed.

Open: No bulk redirect batch or Swim redirect was activated at theme launch.

## 19.6 Open post-launch plan

Open: Confirm GA4 transaction ID 7771369111689 for order #51906 after normal processing.

Open: Confirm the matching Google Ads purchase conversion independently.

Open: Confirm the matching Meta Purchase event independently.

Open: Review Search Console Page Indexing, Coverage and Enhancements after recrawl.

Open: Monitor technical and organic performance at 24 hours, 72 hours, 7 days, 14 days and 28 days.

Open: Build and SEO-check Active, Everyday and Accessories before linking them.

Open: Complete the replacement Swim collection before any canonical or redirect change.

Open: Re-test Essential Upsell and complete Sami Wholesale through supported Broadcast routes.

Open: Complete privacy, Simprosys, Meta CAPI and Barb runtime work under their separate approval gates.

Open: Visually inspect the newest homepage and product Tested for Safety blocks at usable desktop and mobile sizes.

## 19.7 Current release boundaries

Do not infer Google Ads or Meta success from Shopify or GA4.

Do not activate the Swim redirect until the replacement destination is complete and validated.

Do not retire Sense until monitoring closes and rollback retirement is approved.

Do not bulk-edit redirects, shared products, pages, metadata, apps, tracking or Markets without separate approval and read-back verification.

## 19.8 Current evidence

Eltee_New_Website_Migration_Work_Completed_v1.0_2026-08-29.md

Eltee_Broadcast_Go_Live_Checklist_CURRENT_v1.25_2026-08-29.md

BROADCAST_PUBLICATION_AND_SMOKE_TEST_EVIDENCE_v1.0_2026-08-29.md

SOURCE_CONFLICT_REGISTER_v1.11_2026-08-29.md

BROADCAST_SCHEMA_IMPLEMENTATION_EVIDENCE_v1.0_2026-08-28.md

BROADCAST_POST_LAUNCH_ORDER_51906_TRACKING_CHECK_v1.0_2026-08-29.md

FIT_PAGE_CONTENT_RESTORE_EVIDENCE_v1.0_2026-08-29.md

HOMEPAGE_TESTED_FOR_SAFETY_COLUMN_EVIDENCE_v1.0_2026-08-29.md

PRODUCT_PAGE_TESTED_FOR_SAFETY_BLOCK_ROLLOUT_EVIDENCE_v1.0_2026-08-29.md

VERSION_REGISTER.md